## Sprint Backlog
Commited Backlog Items |  |  |  | Status |  |  | Hours
Priority | ID | Name | Sub Task | Not Started | In-Progress | Complete
HIGH | PB_1 | File processing | Read movies.txt and my_ratings.txt |  |  | Complete | 15
HIGH | PB_2 | CLI & Initialization of main | Initialization of objects |  |  | Complete | 3
HIGH | PB_3 | Create Reviews | createReview method |  |  | Complete | 6
HIGH | PB_3 | Recommendation Algorithm | calculate genre scores |  |  | Complete | 4
LOW | PB_4 | Allow user to search reviewed movies | Add getter method to User class | Not Started
HIGH | PB_2 | CLI & Initialization of main | Implement start and main menu CLI interface |  |  | Complete | 8
HIGH | PB_2 | CLI & Initialization of main | Implement User Input |  |  | Complete | 3
HIGH | PB_9 | Test Recommendation Algorithm | Test recommendation algorithm and fill in test documentation |  |  | Complete | 4
HIGH | PB_8 | Test File processing | Test file processing and fill in test documentation |  |  | Complete
HIGH | PB_4 | Allow user to search reviewed movies | Create search algorithm |  |  | Complete
HIGH | PB_10 | Recommendation Algorithm | Separate no review edge case |  |  | Complete | 2
HIGH | PB_11 | Recommendation Algorithm | Calculate overall scores |  |  | Complete | 3