## Sheet1
Product Backlog Items
SNo | Priority | ID | Name | Estimated Hours | Authors
1 | HIGH | PBI_1 | File processing | 10 | David
2 | HIGH | PBI_2 | CLI & Initialization in main | 10 | Marko
3 | HIGH | PBI_3 | Recommendation Algorithm | 10 | Alex
4 | LOW | PBI_4 | User can search their reviewed movies | 4 | *
5 | HIGH | PBI_5 | Making reviews | 4 | Alex
6 | MEDIUM | PBI_6 | Helper function class | 5 | David
7 | MEDIUM | PBI_7 | Commenting Code | 2 | Alex, David, Marko
8 | HIGH | PBI_8 | Test File Processing | 4 | David
9 | HIGH | PBI_9 | Test Recommendation Algorithms | 4 | Alex, Marko

## PBI_9
PBI
ID | PBI_9
Name | Test Recommendation Algorithm
Description | Testing that the recommendation methods return the expected results.
Acceptance Criteria | The actual result of the tests match the expected result or is including with known bugs
Definition of Done | Tested most edge cases. Tested cold start problem, tested recommendations given similar highly rated movies, and recommendation does not include user reviewed movies.
Estimated Effort | 4 hours
PBI Author | Alex, Marko

## PBI_8
PBI
ID | PBI_8
Name | Test File Processing
Description | Testing that the file processing and rating methods return the expected results.
Acceptance Criteria | The actual result of the tests match the expected result or is including with known bugs
Definition of Done | Tested most edge cases. Tested file reading, file writing, and creating ratings.
Estimated Effort | 4 hours
PBI Author | David

## PBI_7
PBI
ID | PBI_7
Name | Comment Code
Description | Include reasonable comments for all methods to improve code clarity.
Acceptance Criteria | All relevant functions are well documented. Anyone who looks at the code should be able to understand what is going on.
Definition of Done | Every relevant function is commented.
Estimated Effort | 2 hours
PBI Author | Alex, David, Marko

## PBI_6
PBI
ID | PBI_#
Name | Helper Class
Description | Class housing different helper methods that other classes utilize
Acceptance Criteria | Helper methods work as intented
Definition of Done | Class performs its job as a helper providing methods to other classes. No other classes require helper methods
Estimated Effort | 1 hour
PBI Author | David

## PBI_5
PBI
ID | PBI_5
Name | Making Reviews
Description | Getting user input and send it to the file handler
Acceptance Criteria | Minimal errors from user input, errors are reported and dealt with.
Definition of Done | Succsefully takes users input and send info to fileprocessing.
Estimated Effort | 4 hours
PBI Author | Alex

## PBI_4
PBI
ID | PBI_4
Name | User can search their reviewed movies
Description | Allows user to search for reviews made using movie title.
Acceptance Criteria | Does not crash with malformed input. Displays correct review.
Definition of Done | Succesfully reads user input and displays correct review. Goes back to main menu if user gives a movie that they have not rated or that does not exist.
Estimated Effort | 4
PBI Author | *

## PBI_3
PBI
ID | PBI_3
Name | Recommendation Algorithm
Description | An algorithm that rates movies based on users highly rated movies.
Acceptance Criteria | Runs with minimal errors. Handles and throws errors properly.
Definition of Done | Algorithm successfully recommends 5 movies that are most similar to users rated movies.
Estimated Effort | 10 hours
PBI Author | Alex

## PBI_2
PBI
ID | PBI_2
Name | CLI & Initialization in main
Description | Handles the command-line interface for user interaction. It is responsible for initializing the system, loading movies and ratings, and creating the User object and RecommendationEngine object. It handles user input for recommendations, reviewing movies, and program termination.
Acceptance Criteria | Displays start and main menu operations clearly. User can perform listed operations. All objects are initialized.
Definition of Done | System runs and user can get recommendations, rate movies, and terminate the program without crashing. All objects are initialized with no bugs.
Estimated Effort | 10 hours
PBI Author | Marko

## PBI_1
PBI
ID | PBI_1
Name | File_Processing
Description | FileHandler class. Handles reading movies.txt, my_ratings.txt and writing to my_ratings.txt
Acceptance Criteria | Reads files even if malformed lines present. Meaningful error messages, file reading doesn't result in crashes
Definition of Done | Sucessfully reads my_ratings.txt and movies.txt and is able to update my_ratings.txt with new reviews
Estimated Effort | 12 hours
PBI Author | David