## Sprint Backlog
Commited Backlog Items |  |  |  | Status
Priority | ID | Name | Sub Task | Not Started | In-Progress | Complete | Hours
HIGH | PB_1 | File processing | Read movies.txt and my_ratings.txt |  | In-Progress |  | 10
HIGH | PB_2 | CLI & Initialization of main | Initialization of objects |  | In-Progress |  | 5
HIGH | PB_3 | Create Reviews | createReview method |  |  | Complete | 4
HIGH | PB_3 | Recommendation Algorithm | calculate genre scores |  |  | Complete | 10
LOW | PB_4 | Allow user to search reviewed movies | Add getter method to User class | Not Started |  |  | 2.5
HIGH | PB_2 | CLI & Initialization of main | Implement start and main menu CLI interface |  | In-Progress |  | 2.5
HIGH | PB_2 | CLI & Initialization of main | Implement User Input |  | In-Progress |  | 2.5
HIGH | PB_9 | Test Recommendation Algorithm | Test recommendation algorithm and fill in test documentation | Not Started |  |  | 4
HIGH | PB_8 | Test File processing | Test file processing and fill in test documentation | Not Started |  |  | 4
HIGH | PB_4 | Allow user to search reviewed movies | Create search algorithm | Not Started |  |  | 2.5
|  | Test Review Functionality | Test Creating reviews and fill in test documentation | Not Started |  |  | 4